## Slide 1: SCOPE MANAGEMENT SECRETS
The Heart of Project Management
Brad Bigelow, PMP
DAY ONE

## Slide 2: Disclaimer
The views and opinions expressed in the following PowerPoint slides are those of the individual presenter.
These PowerPoint slides are protected under the copyright laws of the United States of America and other countries. Used by permission. All rights reserved. Project Management Institute and PMI are registered trademarks. All other trademarks are the property of their respective owners.
The PowerPoint slides are for registered attendees of the PMI® SeminarsWorld®.
2
Scope Management Secrets: Day One

## Slide 3: Learning Objectives
Accurately assess the scope of a project and organize it into well-defined and easily controlled elements
Effectively prepare Project Charters and Project Management Plans primed to ensure visibility, achieve expectations, and deliver results
Anticipate likely sources of scope change and formulate effective responses through change management
Scope Management Secrets: Day One

## Slide 4: Course Overview
Day One: Understanding Scope Management
Day Two: Scope Management through the Project Lifecycle
Scope Management Secrets: Day One

## Slide 5: Day One: Understanding Scope
The Basics
The Not-So-Basics
Why Scope is Fuzzy
Why Scope is Risky
Exercises

## Slide 6: SCOPE MANAGEMENT: The Basics

## Slide 7: Scope Management: At the Heart
Integration
Management
Resource
Management
Quality
Management
Scope
Management
Communi-cations
Management
Procurement
Management
Stakeholder
Management
Schedule
Management
Cost
Management
Risk
Management

## Slide 8: Project Management 101
“A project is a temporary endeavor undertaken to create a unique product, service or result.”

## Slide 9: Project Management 101
“A project is a temporary endeavor undertaken to create a unique product, service or result.”
Finite Time

## Slide 10: Project Management 101
“A project is a temporary endeavor undertaken to create a unique product, service or result.”
Finite Time
Work

## Slide 11: Project Management 101
“A project is a temporary endeavor undertaken to create a unique product, service or result.”
Finite Time
Work
Output

## Slide 12: “The Iron Triangle”
Time
Cost
Scope

## Slide 13
Time and Cost
Scope
Project
Managers

## Slide 14
Time and Cost
Scope
Project
Executives

## Slide 15: Or, to Put Another Way …
Pick any two:
__ Better
__ Faster
__ Cheaper

## Slide 16: Definitions

## Slide 17: PMBOK definition: Scope
“The sum of the:
  Products,
  Services, and
  Results
to be provided as a project.”

## Slide 18: PMBOK definition: Product
“An artifact that is produced, is quantifiable, and can be either an end item in itself or a component item.
“Additional words for products are materials and goods.
“See also deliverable.”

## Slide 19: PMBOK definition: Service

## Slide 20: PMBOK definition: Result
“An output from performing project management processes and activities.
“Results include outcomes (e.g., integrated systems, revised process, restructured organization, tests, trained personnel, etc.) and documents (e.g., policies, plans, studies, procedures, specifications, reports, etc.).
“See also deliverable.”

## Slide 21: PMBOK definition: Deliverable
“Any unique and verifiable product, result, or capability to perform a service that is required to be produced to complete a process, phase, or project.”

## Slide 22: PMBOK definition: Scope Management
“The processes required to ensure that the project includes all the work required, and only the work required, to complete the project successfully.”

## Slide 23: PMBOK definition: Scope Management
“The processes required to ensure that the project includes all the work required, and only the work required, to complete the project successfully.”

## Slide 24: Key Concepts
“Scope can refer to:
Product scope
  The features and functions that characterize a product, service, or result
Project scope
  The work performed to deliver a product, service, or result.”

## Slide 25: Key Concepts
“Scope can refer to:
Product scope
  The features and functions that characterize a product, service, or result
Project scope
  The work performed to deliver a product, service, or result.”
The What
The How

## Slide 26: Changes: PMBOK 6th to PMBOK 7th

## Slide 27: Changes: PMBOK 6th to PMBOK 7th

## Slide 28: System for Value Delivery
External environment
Internal environment
Operations
System for Value Delivery
Portfolio
Portfolio
Program
Projects
Program
Program
Projects
Projects
Projects
Projects
Program
Projects

## Slide 29: System for Value Delivery
External environment
Internal environment
Operations
System for Value Delivery
Portfolio
Portfolio
Program
Projects
Program
Program
Projects
Projects
Projects
Projects
Program
Projects
All Projects Exist within a Context

## Slide 30: System for Value Delivery
External environment
Internal environment
Operations
System for Value Delivery
Portfolio
Portfolio
Program
Projects
Program
Program
Projects
Projects
Projects
Projects
Program
Projects
CHANGING
CHANGING
CHANGING
CHANGING

## Slide 31: Classic Scope Definition Elements
Work Breakdown Structure (WBS)
Product Breakdown Structure (PBS)

## Slide 32: The Simplest Project Model Ever
Inputs
Work
Outputs

## Slide 33: The Simplest Project Model Ever
All of this is SCOPE
Inputs
Work
Outputs

## Slide 34: Work Breakdown Structure (WBS)
“A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.”
In Other Words:
The WBS describes HOW the Project will deliver its outputs

## Slide 35: WBS Example
Build Bicycle
Assemble Frame & Cotrols
Manage Project
Assemble Power Train
Assemble Wheels
Integration
Assemble Brakes
Frame
Handlebars
Fork
Seat
Fenders

## Slide 36: WBS Example
Build Radio Station
Purchase Land
Manage Project
Construct Building
Install Equipment
Transition to Operations

## Slide 37: WBS Example
Implement Financial Software
Install Software
Manage Project
Configure Forms and Workflows
Migrate Data
Transition to Operations
Train Users

## Slide 38: Product Breakdown Structure (PBS)
A hierarchical decomposition of all the products to be products by a project.
In Other Words:
The PBS describes WHAT outputs the Project will deliver

## Slide 39: PBS Example
Bicycle
Frame & Controls
Power Train
Wheels
Brakes
Frame
Handlebars
Fork
Seat
Fenders

## Slide 40: WBS/PBS Linkage
Radio Station Equipment
Broadcast
Radio
Antenna
Studio Equipment
Ancillary Equipment
Furniture
Computers & Comms
Power Supply
Generator
Racks & Cabling

## Slide 41: Project Math 101
WBS + PBS = Project Scope

## Slide 42: Project Math 101
WBS + PBS = Project Scope
What happens if the PM can’t allocate a requirement to the WBS or PBS?

## Slide 43: WBS
Radio Station Equipment
Broadcast
Radio
Antenna
Studio Equipment
Ancillary Equipment
Furniture
Computers & Comms
Power Supply
Generator
Racks & Cabling
How
What
Project Scope should almost always be described in BOTH terms
PBS

## Slide 44: WBS
Radio Station Equipment
Broadcast
Radio
Antenna
Studio Equipment
Ancillary Equipment
Furniture
Computers & Comms
Power Supply
Generator
Racks & Cabling
How
What
Project Scope should almost always be described in BOTH terms
PBS
Which comes first?
The Products?
Or the Work?

## Slide 45: Product-Based Project Planning
Define and Analyze Products
Organize Work Packages
Prepare Estimates
Prepare Schedule
Prepare Budget
Document the Plan
Analyze Risks

## Slide 46: Work-Based Project Planning
Define & Organize Necessary Work
Define Products & Allocate to Work
Prepare Estimates
Prepare Schedule
Prepare Budget
Document the Plan
Analyze Risks

## Slide 47
“Projects don’t GO wrong. They START wrong.”

## Slide 48: Back to the Triple Constraint
Time
Cost
Scope
If this increases
Then so must one or both of these
Scope Management Secrets: Day One

## Slide 49: WBS Impacts on Schedule
Build Radio Station
Purchase Land
Manage Project
Construct Building
Install Equipment
Transition to Operations
Duration
Sequencing
Critical
Path

## Slide 50: PBS Impacts on Schedule
Lead Time
Dependencies

## Slide 51: WBS Impacts on Cost
Build Radio Station
Purchase Land
Manage Project
Construct Building
Install Equipment
Transition to Operations
Procurement
Costs
Activity
Costs
Activity &
Procurement
Costs
Activity &
Procurement
Costs

## Slide 52: PBS Impacts on Costs
Procurement Costs
Procurement Costs
Procurement Costs
Procurement Costs
Procurement Costs
Procurement Costs

## Slide 53: Impacts on Risk
WBS:
  Critical path
  Overruns in duration, activity cost
PBS:
  Interdependencies
  Overruns in cost, delivery time

## Slide 54: Impacts on Stakeholder Engagement
WBS:
  Which stakeholders are involved?
  How they are involved?
  Is stakeholder engagement part of the WBS as a project management activity?
PBS:
  Producers/suppliers are stakeholders

## Slide 55: Impacts on Change Management
WBS:
  Reflects the project approach: change friendly? Change averse?
  Changes in scope linked to WBS elements
PBS:
  Also reflects the project approach: is it locked in or flexible?

## Slide 56: Scope Management: At the Heart
Integration
Management
Resource
Management
Quality
Management
Scope
Management
Communi-cations
Management
Procurement
Management
Stakeholder
Management
Schedule
Management
Cost
Management
Risk
Management

## Slide 57: Key Concepts: Project Lifecycle
“Projects can range along a continuum from Predictive approaches at one end to Adaptive or Agile approaches at the other.”

## Slide 58: Predictive
Scope
Time
Cost
Determined early in the project
Baselined
Changes carefully managed

## Slide 59: Iterative
Scope
Determined early in the project
Time
Cost
Modified as understanding of the product increases

## Slide 60: Agile
Scope
Which deliver and clarify
Time
Cost
Increments (sprints) of work

## Slide 61: Scope Management Process
Plan Scope Management
Collect Requirements
Define Scope
Create WBS (and PBS!)
Validate Scope
Control Scope

## Slide 62: Scope Management Process
Monitoring & Controlling
Planning
Plan Scope Management
Collect Requirements
Define Scope
Create WBS
Validate Scope
Control Scope

## Slide 63: Key Inputs
Project Charter
Project Documentation
  Assumption Log
  Risks Register
  Stakeholder Register
Project Management Plan
Enterprise Environment Factors
Organizational Process Assets

## Slide 64: Key Outputs
Scope Management Plan
WBS
Requirements Documents
Inputs to Assumptions Log
Inputs to Stakeholder Register
Change Requests

## Slide 65: Tailoring Considerations
Knowledge Management
Requirements Management
Validation
Control
Development Approach
Stability of Requirements
Governance

## Slide 66: Scope Management Plan
Preparing the Scope Statement
Creating the WBS
Scope Baseline approval and maintenance
Formal acceptance

## Slide 67: Requirements Management Plan
Collection
Analysis
Tracking
Prioritization
Traceability
Change management
Reporting

## Slide 68
Scope Management
Plan
Scope
Management
Create
WBS
Control
Scope
Collect
Requirements
Define
Scope
Validate
Scope
Scope Management Secrets: Day One

## Slide 69: The Relocation Project
Accounting
Human Resources
New Location

## Slide 70: Exercise #1: Defining Scope
You are the PM for the Relocation Project.
Prepare an initial Project Scope Statement:
  Work Breakdown Structure
  Product Breakdown Structure
  List of Planning Assumptions

## Slide 71: SCOPE MANAGEMENT: The Not-So Basics WHY SCOPE IS COMPLEX

## Slide 72: The Project Life Cycle
Initiation
Planning
Carrying Out the Work
Closing

## Slide 73: The Larger Life Cycle
What is Going On During the Project
What Happened in the Past
What Led to Project Initiation
What will Happen After the Project

## Slide 74: Project as Change Delivery
Organizational Strategy
Business as Usual
New Business as Usual
Project

## Slide 75: The Larger Life Cycle
What is Going On During the Project
What Happened in the Past
What Led to Project Initiation
What will Happen After the Project
Enterprise Environmental Factors
  Organizational culture
  Infrastructure
  Personnel
  Market Forces
  Regulations
  Organizational Process Assets

## Slide 76: What is the Project’s Why?
Why are we doing this?

## Slide 77
“If you don't know
where you are going,
you'll end up
someplace else.”

## Slide 78: Project Initiation Context
Regulatory/Legal/
Social Requirements
Stakeholder Needs
Create New Products, Processes or Services
Upgrade/Improve/
Refresh Existing Capabilities
Transformational Change
One or More of These is the Source of the Project’s WHY

## Slide 79: The Basic “Why” Model
Projects deliver outputs
The outputs enable outcomes
The outcomes realize benefits
The benefits achieve strategic objectives

## Slide 80: A Benefits Model
Radio
Station
Improved
Public
Communication
Output
Benefit
Outcome
More Stable Public Security
Enables
Realizes
Project
Delivers

## Slide 81: Outputs versus Benefits
1903
2003
Output
Benefits

## Slide 82: Two ways to see the project

## Slide 83: Looking forward:
What has to be done?
What has to be delivered?
The PM’s View

## Slide 84: Looking backward:
What have been the outcomes?
What have been the benefits?
The Sponsor’s View

## Slide 85: How Time Can Affect Scope
1964
2014
By What Timeframe
will the
Project be Judged?
Short Term?
Or Long Term?

## Slide 86: Ecosystems and Interests

## Slide 87: Scoping the Scope
How can you plan Scope Management if any of the following are missing from the Project Charter?
  Purpose
  Measurable Objectives and Success Criteria
  High-level project description, boundaries, and key deliverables
  Project approval criteria (e.g, what constitutes project success)?

## Slide 88: Scope in the Project Charter
“The Scope section addresses the Who, What, Where, When, and Why of a project.”*
*Most of the Project Charter templates you will find on the Internet

## Slide 89: Scope in the Project Charter
“The Scope section addresses the Who, What, Where, When, and Why of a project.”*
*Most of the Project Charter templates you will find on the Internet
And the How!

## Slide 90: Work Scope vs. Product Scope
The WBS (the “How” of Delivery)
The PBS (the “What” of Outputs)

## Slide 91: Work Aspects: Change Approach
Green Field?
  Little or no existing infrastructure, least impact on current operations
Upgrade/Improvement?
  Backwards compatibility, synchronization with existing operations, before/after comparisons
Transformational?
  Transition from “As Is” to “To Be,” slack in transforming workforce, before/after comparisons

## Slide 92: Work Aspects: Project Lifecycle

## Slide 93: Work Aspects: Project Model
Each Model carries Assumptions and Constraints for both the WBS and the PBS

## Slide 94: Adaptive/Agile/Incremental
How will the approach be reflected in the Work Breakdown Structure?
Or will the WBS (and PBS?) be updated and re-baselined repeatedly?
Are prototypes and other interim deliverables also part of the Product Breakdown Structure?

## Slide 95: Project team
Aspects to consider:
  Co-located? Dispersed? Virtual?
  Do they share a common language? Culture? Time Zone?
  What is the level of commitment of team members?
  What are their Priorities? Constraints?
  What is their level of authority?
  What is their level of expertise/experience?

## Slide 96: Sourcing/Procurement
Sourcing Decisions:
  In-house? • Equipment?
  Outsourced? • Services?
  Mix? • Mix?
Very often, procurement must be included as part of the WBS
  But procurement approach can also influence the PBS

## Slide 97: Contractors as part of the project team
How are they contributing?
  As suppliers?
  As developers?
  As producers?
  As integrators?
  As workforce capacity?
  As consultants/subject matter experts?
  Onsite? Offsite?
  Some or all of the above?
Scope Management Secrets: Day One

## Slide 98: Transition/Handover
Tied to the change model (e.g., Green Field)
Transition impacts on WBS (and PBS?):
  Workforce training/retraining
  New/adapted procedures
  Parallel operation (old/new)
  Fallback option
  Initial operational support

## Slide 99: Product Aspects
PBS and its components
  Sourcing
  Buy? Assemble? Develop? Integrate?

## Slide 100: Individual Product Requirements
Physical Scope
Quality
Control requirements
Acceptance criteria

## Slide 101: Defining the Outputs/Deliverables
Production outputs
  What most customers consider outputs: the things they will use
Management outputs
  What are needed to plan, monitor, and control the project

## Slide 102: Physical scope
Quantity
Size
Capacity
Location

## Slide 103: Quality
Functional requirements
    What the product needs to do
Nonfunctional requirements
    What the product needs to be
    Often referred to as the “ilities”
      Reliability
      Availability
      Maintainability

## Slide 104: Product control requirements
Design/development/production checkpoints
Inspection
Testing
Inventory

## Slide 105: Acceptance criteria
Who accepts?
What?
When?
Where?
How?
A key link to the WBS

## Slide 106: Other Aspects of Scope
Boundaries
Constraints
Sustainability
Change Appetite
Volatility (e.g.,Market, Organization, Technology)
Time

## Slide 107: Boundaries
Where does the project stop?
You Should Be Able to Tell What’s
Out of Scope
If You Know What’s In Scope

## Slide 108: Constraints
Authority
  What Project Manager has authority to decide
Legal
  What means are considered legal?
Regulatory
  Are there health and safety constraints?
Interfaces
  Do the products have to work with other systems?
Policy
  Are there policy constraints on how the work is done?
Operational
  Are there constraints on disrupting running operations?

## Slide 109: Sustainability

## Slide 110: Governance
Who/What does the Project Manager report to?
  Internal Project Management
  Project Board
  Project Sponsor
  Program Management Office
  Corporate Board or Committee
  Public Board or Committee
Are there any back-channels? Do they matter?

## Slide 111: Program management/PMO
Is the project part of a program?
How that impacts scope
  As an enabler
  As a constraint

## Slide 112: Decision Making
Who can approve changes to:
  Project Scope Baseline?
  Contracts and Agreements?
  Project Budget?
  Project Schedule?
And how fast do these processes work?

## Slide 113: Volatility
How susceptible is the project to:
  Change from within the project?
  Change from outside the project?

## Slide 114: Change Appetite
Open to Experimentation
Leaning Forward
Resistance
&
Inertia
“The Spirit is Willing but the Flesh is Weak”
Urgency
Readiness
Low
High
Low
High
What Can the Project
Expect To Encounter?

## Slide 115: What is the Appetite for Change?
Change?
Scope Management Secrets

## Slide 116: Importance of a Holding Space
Early in the Project Life Cycle, it’s not always clear what’s In Scope and Out of Scope
Deciding too early can lead to problems with Planning, Execution and Acceptance
Provide a space to hold what’s in doubt
    This can be one function of the Issue Log

## Slide 117: Baselining Scope
As part of Project Management Plan approval, its Scope should be baselined:
  WBS
  PBS
  Requirements Documents
This is key to enable Change Management and Reporting

## Slide 118: Baselining: Establishing Controls
In Scope
Not in Scope

## Slide 119: Group Exercise #2: Revising Scope
In light of the preceding discussion, how should we revise the Initial Project Scope Statement for the Relocation Project?
Do we need to make changes in:
  The Work Breakdown Structure to the first level (major activities)?
  The Product Breakdown Structure?
  The list of planning assumptions?
Is there anything we should place into a Holding Space such as the Issue Log?

## Slide 120: SCOPE MANAGEMENT: The NOT-So BASICS WHY SCOPE IS FUZZY

## Slide 121: Time is Easy to Measure
Start
Planned
Actual
Finish
Start
Finish
Early
Late
200 days
200 days
210 days

## Slide 122
Planned
Actual
Over
Under
$200,000
$200,000
$225,000
Cost is Easy to Measure
Scope Management Secrets: Day One

## Slide 123: Scope?
Planned
Actual
Over
Under
What number would apply?
???
There is no single measure for scope
Scope Management Secrets: Day One

## Slide 124: A Set with a Clear Boundary

## Slide 125: A Set with a Fuzzy Boundary

## Slide 126: A Fuzzy Set: Tall Basketball Players
Manute Bol
7 ft. 7 in.
Muggsy Bogues
5 ft. 3 in.
Jason Kidd
6 ft. 4in.
Dirk Nowitski
7 ft.
Josh Howard
6 ft. 7 in.

## Slide 127: Q: Where Do Requirements Come From?
A: Stakeholders!
This is why Stakeholder Identification and Analysis should be the first step in the process

## Slide 128: Who’s a Stakeholder?
An individual, group, or organization that may be:
  Involved in
  Affected by
  Able to affect
  Have an interest in
  Have an opinion about
}
The Project
or
Its Outcomes

## Slide 129: Stakeholders
Have an interest in or Opinion about
Are Affected By
Are Involved In
The Project Team

## Slide 130: Stakeholder Analysis
Interests
Influence
Authority
Rights
Ownership
Knowledge
Contribution
Means to Communicate/Engage

## Slide 131: Stakeholder Engagement
The Key is to Understand that Requirements Elicitation and Validation is a Social Activity
Participation Always Improves Buy-In

## Slide 132: Stakeholder Engagement: Getting Buy-in
The impact of time/distance/commitment
Mitigating the risk of rejection
Never underestimate the value of spending long hours together in conference rooms (or on Zoom)!

## Slide 133: Collecting Requirements

## Slide 134: Requirements Elicitation
Interviews
Role-Playing or Simulation
Brainstorming
Questionnaires
Focus Groups
Prototyping
Observation

## Slide 135: The Challenge of Requirements Elicitation
The Project’s
Perspective
The Stakeholder’s Perspective
It is hard to find someone with 20/20 vision in both

## Slide 136: What’s a Message?
Scope Management Secrets: Day One

## Slide 137: Requirements Elicitation
Never underestimate the value of a conference room wall covered in Post-It® notes!

## Slide 138: Requirements Elicitation/Collection
Elicitation often involves delving into the stakeholder’s unconscious:
  Expectations
  Assumptions
  Fears
  Opposition
Scope Management Secrets: Day One

## Slide 139: Requirements Elicitation/Collection
In an Ideal World, Requirements would be delivered on a Silver Plate:
  SMART
  Complete
  Validated
  Owned
  Explicit
  Unambiguous

## Slide 140: Requirements Elicitation/Collection
In the Real World, Requirements are rarely more than some of these:
  SMART
  Complete
  Validated
  Owned
  Explicit
  Unambiguous

## Slide 141: Requirements Analysis
Elicitation& Collection
WBS
PBS
Analysis
Holding
Space
Rework
Hold
Allocate
Reject
Allocate
System
Requirements Specification

## Slide 142: Requirements Validation
The Requirements Documentation is almost always assembled from the inputs of multiple stakeholders with varying interests
If possible, make sure someone takes ownership and validates the requirements
  Avoid the ugly “Who asked for this?” questions

## Slide 143: Traceability: Deriving vs. Inventing
Charter
Project Management Plan
Requirements Baseline (WBS, PBS)
Statements of Work
Product Specifications
A few pages
25-50 pages
25-50 pages
10s to 100s of pages
10s to 1,000s of pages

## Slide 144: Requirements quality control
The theory of SMART requirements
  Specific
  Measurable
  Attainable
  Relevant
  Timely
High Quality Requirements = High Quality Results

## Slide 145: The reality of SMART requirements
The theory of SMART requirements
  Specific
  Measurable
  Attainable
  Relevant
  Timely
High Quality Requirements Do Not Guarantee High Quality Results
Quality Has a Cost
Few Projects Succeed in Obtaining SMART Requirements across the full project scope

## Slide 146: Tom Gilb’s Challenge
“The Top 10 Critical Requirements for any project can be identified and quantified in a good day’s work— and written down on a single page.”
Scope Management Secrets: Day One

## Slide 147: Group Exercise #3: Requirements
Identify one Top Ten Critical Requirement
Quantify it
Write it down in no more than 3 sentences
The Tom Gilb Challenge

## Slide 148: Requirements Change Analysis
Elicitation& Collection
WBS
PBS
Analysis
Holding
Space
Rework
Hold
Allocate
Reject
Allocate
System
Requirements Specification
New Require-ment

## Slide 149: The Integrated Project Baseline
Time
Cost
Scope
If this increases
Then so must one or both of these
Baseline Schedule
Baseline Budget
Scope Baseline

## Slide 150: Change control
Time
Cost
Scope
If this increases
Then so must one or both of these
Baseline Schedule
Baseline Budget
Scope Baseline
Change
Evaluate Changes in Terms of Changes to the Baselines

## Slide 151: Third Law of Motion
Rejecting a change has a consequence.

## Slide 152: What Happens to Change that Falls Out of Scope?
Scope Management Secrets: Day One

## Slide 153
How do you deal with project change?

## Slide 154: SCOPE MANAGEMENT: The NOT-So BASICS WHY SCOPE IS RISKY

## Slide 155
I predict that people will continue to be terrible at making predictions.
Scope Management Secrets: Day One

## Slide 156: Know What/Know How Matrix
Scope Management Secrets: Day One

## Slide 157: Know What/Know How Matrix
Product Immaturity

## Slide 158: Know What/Know How Matrix
Process (Work) Immaturity

## Slide 159: Maturity
Have we done this type of work before?
Have we dealt with this type of product before?
If not … Is there anyone we can copy learn from?

## Slide 160
How does know how/know what maturity affect your projects?
Q:
Scope Management Secrets: Day One

## Slide 161: Uncertainty
Known
Unknowns
Known
Knowns
Unknown
Unknowns
Unknown
Knowns

## Slide 162: Uncertainty: Explicit and Implicit
Explicit:
  Whatever is not stated must therefore be uncertain
Implicit:
  Whatever is stated imprecisely or unclearly must therefore incorporate some uncertainty

## Slide 163: Impact of Duration
Planning
Completion
Scope Management Secrets: Day One

## Slide 164: Impact of Duration
Planning
Completion
Scope Management Secrets: Day One

## Slide 165: Cognitive Biases
Groupthink
Overconfidence
Selective Perception
Sunk Cost
Illusion of Control
Available Data

## Slide 166: Cognitive Biases
Humans tend to be overly optimistic about future benefits
Humans tend to be overly pessimistic about future losses
The farther away the target, the greater this effect can be seen

## Slide 167: Organizational Culture
Formal and Hierarchical?
Informal and Cooperative?
Scope Management Secrets: Day One

## Slide 168: Risk Appetite
Scope Management Secrets: Day One

## Slide 169: Elephants and Risks
Just pretend I’m not here.

## Slide 170: Elephants and Risks
“Let Sleeping Elephants Lie”
“It’s not MY Elephant!”
“What Elephant?”
“The Boss Says There’s No Elephant”
“Maybe the Elephant Will Just Go Away”
“This isn’t an Elephant: It’s an Opportunity!”
Inertia
Ownership
Denial
Influence
Wishfulness
Overconfidence
Courtesy of Kailash Awati, https://eight2late.wordpress.com/

## Slide 171: Group Exercise #4: Scope Risks and Responses
Think about the Relocation Project:
  Identify two High Risks of Uncertainty or Scope Change
  Propose two Responses or Ways to Mitigate each

## Slide 172: The Cone of Uncertainty
Too High
Too Low
Initiating
Planning
Executing
Acceptance
Estimation
Uncertainty

## Slide 173: All Estimates are Uncertain
Lack of adequate data
Inappropriate comparisons
Misjudged parameters
Missing elements
False precision
Mandated by decree
This is why professional estimates come with confidence levels or margins of error
Scope Management Secrets: Day One

## Slide 174: The Cone of Uncertainty
Too High
Too Low
Initiating
Planning
Executing
Acceptance
Estimation
Uncertainty
Margin of Error

## Slide 175: Risk & Cost of Change over Time: Theory
Time
Risk
Cost of Changes

## Slide 176: Risk & Cost of Change: Reality
Time
Risk
Cost of Changes
Project
Baselined

## Slide 177: Dealing with uncertainty
Define it out—or define it in
Plan it out—or plan it in
Reduce it incrementally
Reduce it agilely
Eliminate it through renegotiation
Ignore it and hope for the best …

## Slide 178: Mitigation measures:
Estimates with confidence levels/margins of error
Contingency budget
Change budget
Tolerances
Costed Risks
Adaptive Life Cycle
Rolling Backlog
Scope Holding Pen
Most Important of All:
Constant
Communication!

## Slide 179: Mitigating Risk & Cost of Change
Time
Risk
Cost of Changes
Project
Baselined
Approved &
Allocated Budget
PM’s Reserve
Approved Change Budget
Sponsor’s Reserve
Trade Space

## Slide 180: Project Management 101
“A project is a temporary endeavor undertaken to create a unique product, service, or result.”

## Slide 181
So, projects are all about deliverables, right?

## Slide 182: The Basic “Why” Model
Projects deliver outputs
The outputs create results
The results realize benefits
The benefits achieve strategic objectives

## Slide 183
Managing Successful Programmes

## Slide 184
Managing Successful Programmes
Delivering the Change

## Slide 185
Managing Successful Programmes
Delivering the Change
Embedding the Change

## Slide 186: Project as Change Delivery
Organizational Strategy
Business as Usual
New Business as Usual
Project

## Slide 187
Relocated
Reduced O&M
Output
Benefit
Result
Increased
Proficts
Project
Project
Delivering the Change
After the Project
Embedding the Change

## Slide 188
Relocated
Reduced O&M
Output
Benefit
Result
Increased
Proficts
Project
Project
Delivering the Change
After the Project
Embedding the Change
Is the Project Life Cycle Too Short?

## Slide 189
Relocated
Reduced O&M
Output
Benefit
Outcome
Increased
Proficts
Project
Project
Delivering the Change
After the Project
Embedding the Change
Or Are We Just Missing the Links?

## Slide 190: Example: A New Cultural Center

## Slide 191: Is this the End of the Project?

## Slide 192: Or the Start of the Outcomes?

## Slide 193: Years Later ….

## Slide 194: Delivering the Change…

## Slide 195: Delivering the Change…
Vs. Embedding the Change

## Slide 196: Results Are What’s Created When the Change Has Been Embedded
Outputs
Outcomes
Benefits

## Slide 197
How Can Projects Help to Embed the Change?

## Slide 198
So, projects are all about deliverables, right?
Outcomes

## Slide 199
Doctrine
Organization
Training
Material
Logistics
Personnel
Facilities
DOTMLPF
Used by US Military and NATO
Translating Outcomes Into Outputs

## Slide 200
Process
Organization
Technology
Information
POTI
Used in ITIL and Managing Successful Programmes
Translating Outcomes Into Outputs

## Slide 201: Q: When is a Project Done?
When its deliverables have created Outcomes!
A:

## Slide 202: Day One Lessons Identified Discussion
What have you found useful?
What can you take away to use on your projects?
Are there any topics we need to deep-dive into?

## Slide 203: Questions?
Scope Management Secrets: Day One

## Slide 204
THANK YOU!
PMI is interested in hearing about your PMI Training experience!
Your input is extremely important in helping us to continuously improve our program.
An email will be sent to you at 3:00pm local time on the last day of your training. The email will come from events@pmi.org
Class time will be provided to allow you to respond.
The survey will take approximately 10 minutes to complete.
Notes: Instructor Note - **PLEASE DO NOT REMOVE THIS SLIDE. THIS IS A REQUIRED SLIDE.**
Instructor Note – Your onsite meeting planner sends this at 3pm the last (or only) day of your training. Please allow time for attendees to complete as the evaluation will provide feedback on their experience in your training.